# Annex 3

# Tentative roadmap for consultations related to the Third edition of the Bologna Policy Forum (BPF3)

| Timeline | Consultation activity | Result |
| --- | --- | --- |
| Sept – Oct 2010 | General consultation with the BFUG and national contact points (NCP) for the themes of the BPF3 | Overview of themes proposed for BPF3 |
| 18 January 2011 | IO WG meeting Vienna: Input for programme/ content of BPF3 (discussion on the feedback received from the NCP) Update on IPN and discussion on roundtable for enhancing European-level promotion Prepare update for BFUG | Proposal for a limited number of BPF3 themes to the BFUG Update for the March 2011 BFUG meeting in Hungary |
| 25 Jan – 20 Feb 2011 | Consultation with the NCP regarding the restricted list of thematic options endorsed by the IO WG meeting on 18.01.2011 and the latest version of the BPF3 agenda | Overview of NCP feedback |
| 17-18 March 2011 | BFUG meeting Budapest Decision on a possible overarching BPF3 theme and endorsing the latest version of the BPF agenda and the IO WG update | Possible overarching theme of the BPF3 and draft agenda |
| April – May 2011 | Informing the NCP about the BFUG decisions (BPF3 possible overarching theme and agenda) Consultation with the NCP on the BPF3 WS themes, ideas for possible speakers and the BPF3 statement | Feedback on WS themes, ideas for possible speakers and for the BPF3 statement |
| 19 June 2011 | IO WG meeting Brussels Discussing the feedback received on WS themes and possible speakers Discussing the impact of the Reporting exercise on the BPF WS themes and speakers Discussing the BPF3 statement Updates regarding the IPN Discussing the final report of the IO WG to the BFUG | Revised WS themes and list of possible speakers Proposal for the main points of the BPF3 statement Structure of the IO WG report to the October 2011 BFUG in Krakow |
| June – Sept 2011 | Circulation of possible changes made in the IO WG meeting to the WS themes, the BPF3 agenda and speakers, as well as the main points of the BPF3 statement | Possible additional feedback from NCP |
| 13-14 October 2011 | BFUG meeting Krakow Endorsing latest BPF3 agenda, WS themes and speaker proposals Endorsing the main points for the BPF3 statement | BPF3 agenda, WS themes and speaker proposals BPF3 statement main points |
| November 2011 | IO WG meeting (Bucharest) BPF3 draft statement discussion WS themes - discussions BPF3 background materials | BPF3 draft statement WS themes proposals BPF3 background materials |
| October – December 2011 | Consulting the NCP on BPF3 draft statement and WS themes | Feedback on BPF3 statement and WS themes |
| 18-19 January 2012 | BFUG meeting Copenhagen Discussions on BPF3 statement, together with the received feedback Endorsing the WS themes, the speakers’ proposals and the Manual for the BPF3 (MBPF) | BPF3 statement new draft WS themes and speakers’ proposals endorsement Manual for the BPF3 (MBPF) |
| January – February 2012 | Consultation with the NCP on the BPF3 draft statement and circulating the MBPF | Feedback on the BPF3 statement |
| 21-22 March 2012 | BFUG meeting Copenhagen Final endorsement of the BPF3 detailed agenda Additional feedback on BPF3 statement | BPF3 detailed agenda Possible changes to the BPF3 statement |
| End of March-April 2012 | Final circulation to the NCP of the final detailed agenda and the final statement before its discussion in the BPF3 | Announcements of possible proposals for amending the BPF3 statement |
| 26-27 April 2012 | Third Bologna Policy Forum (BPF3) | 3rd BPF Statement Parallel sessions reports |